## Slide 1: HMOC update
Sylvain Lodiot
HERA Spacecraft Operations Manager
19-20/11/2024
ESAC

## Slide 2: Outline
HMOC GS status
Pending reviews
Planned Hera activities till end 2025
Technical notes (excel sheets): status
HMOC team composition
Conclusions
MSB

## Slide 3: HMOC GS status
Mission Control System (OPMCS) SCRs expected due to new cubesat commanding functionality)
EDDS/GFTS in place
Simulator supported sims campaign; will be augmented with functions needed for the asteroid phase (minimum needed by FCT)
Mission planning system tool is used since end of LEOP; programs HYP observations already (ahead of schedule)
IGSTs (Integrated Ground/Space Functions Tests, on the bench) and SVTs (System Validation Tests, on the SC)
  SVTs Complete
  Further IGSTs needed (Exp-M mode testing/ISL/PALT/SMC/New CSW); dates TBD

## Slide 4: Pending reviews (till end 2025)
NECR P1 12/12/2024
NECR P2 TBD, post MSB once CSW 2.1 is on board
AODR (Asteroid Operations Design Review), June 2025
  Review the status of post launch developments and the (delta-)design elements of the ground segment (planning concepts, interfaces, delta developments)
AOIR (Asteroid Operations Implementation Review), End 2025
  Ensure ground segment readiness to proceed with Asteroid Operations system validation activities

## Slide 5: Activities till end 2025
Thermal charac completion Next week
Reboot on CSW 1.4 09/12/2024
NECR P1 12/12/2024
PL checkout Feb 2024
MSB 12/12/2024
Reboot on CSW 2.1 post MSB, date TBC
PL checkout 2 week 38/2024
Cubesat checkouts TBD; unique date in December has been proposed

## Slide 6: Cruise TN status
Concerning the cruise TN (excel sheets):
  Good initial experience with NECP
  Need to improve feedback to instrument teams
    Proposal to be done via regular FECS and generation of MTP products (ex FDPM)
    Exchange of excel sheets with (FDPM) event IDs defined
    See MSB slides tomorrow for proposal of an MTP process
  Next Steps:
    One to one meetings for MSB excel entries (and other cruise entries)
  PALT -> nothing received; will not be operated before CSW 2.1 post MSB
Mars flyby is being prepared by HMOC
  See MSB slides; HMOC will lead the full definition of this phase

## Slide 7: Asteroid phase TN status
  Good status for AFC/Hyperscout/RSI
  Nothing for PALT
  Will need to start for TIRI
  See MSB slides
  Work there to resume Q3 2025 TBC

## Slide 8: HMOC status (1)
Team composed of 11 people at launch
  Thomas Dressler -> will leave the team at the end of the year
  Ritchie Kay
  Lisa Savarieau
  Klara Spieker -> will leave the team at the end of January 2025
  Mauro Bartesaghi -> will leave the team at the end of the year
  Charlie Guerbuez
  Gabriel Mihail, database analyst -> now supported by Rudy Ciarletta
  Daniel Lakey joining for LEOP only -> will leave the team at the end of the year
  Anna Schiavo -> replacing Mauro
  Johannes Bauer -> replacing Thomas
  TBA -> replacing Klara
  Myself

## Slide 9: HMOC status (2)
Each team member is/will be allocated an instrument
Due to number of changes, work re-allocation is needed
  Tasks till end of mission defined and are being allocated
Reminder: quiet cruise hoped for to prepare for the asteroid phase
  With NECP soon over, focus will be on MSB (see MSB slides)
  Second half of 2025 dedicated to asteroid phase preparation (expected to be quiet)
  Multiple CSW versions in preparation
  CSW 1.4 expected to be loaded on the SC on 09/12
  CSW 2.1 TBD post MSB

## Slide 10: Conclusion
FCT will now focus on MSB
Then focus on the asteroid phase
Quiet cruise is needed
Good progress of instrument excel sheets, promising work mechanism for the asteroid phase

## Slide 11: MSB agenda
Fly-by Geometry
Deimos observation
Timeline around CA
Overall Timeline and implementation
Way forward
Conclusions

## Slide 12: Fly-by Geometry and driving SC constraints
Mars CA 2025-03-12T12:51 (9070km from centre)
Fly-by plane is shown to the right with Phobos and Deimos orbit
  Shown is +-1h from CA. Very fast fly-by (9km/s)  little time to accommodate all requests and high SC rates needed
    Current operational limit is 0.05deg/s, but pointing degradation can happen at lower values.
  (projected) Sun direction is downwards and 5deg above the image plane
  Sun-SC-Mars angle varies between 5 and 175deg.
    40deg and higher are allowed
    below 40deg conditional constraints become active
    22deg is a hard limit (Hyperscout)
     Pointing to objects has to stop soon after CA.

## Slide 13: Deimos Observation
Baseline is to implement the observation with an inertially fixed pointing at 1024km distance to Deimos (@Mars CA –42min; Deimos CA is at -40min from Mars CA)
at that time:
  Deimos appears as seen from Hera in front of the Mars disk
  moves 0.15deg/s wrt SC  Deimos passes AFC FOV in 38sec
It was investigated whether the constraint envelope (0.05deg/s max) can be extended, but it was found that the SC leaves fine tracking (even at lower rates). Therefore it is recommended to stay with the baseline of an inertially fixed pointing
Open point: how long shall the pointing be kept for Hyperscout and TIRI?

## Slide 14: Timeline around Mars CA
  -92min: Mars fills AFC FOV
  -40min: Deimos CA (300km)
  -7min: rate limit (0.05deg/s) exceeded for Mars pointing (fine pointing may be lost before)
  +14min: Phobos CA (12100km)
  +20min: Sun-SC-Mars angle below 40deg (conditional constraint violated)
  +40min: Sun-SC-Mars angle below 22deg (hard constraint violated)
  +45min: Sun-SC-Phobos angle below 40deg (conditional constraint violated)
  +85min: Sun-SC-Phobos angle below 22deg (hard constraint violated)
Envisaged Pointing Timeline: Mars-Phobos-mid-point, Deimos, Mars, Phobos (?)
Open points:
1) which limiting angle shall be used after Mars CA (e.g. 40deg, 22deg,…)?
2) Which preference of whether and when to slew to Phobos? Consider the following: -the planned feature tracking test may take time for Mars observations
-Slew from Mars to Phobos pointing use a significant part of the gained time

## Slide 15: Overall Timeline
  Standard GAM timeline:
    TCM slots at -4w, -2w, -1w, +1w, emergency slots at -3d and –6h
    Flight rules to be defined for the usage of the emergency slots
  Mars pointing starting from –2 weeks but interrupted by passes
  Pointing during CA: Mars-Phobos-mid-point, Deimos, Mars, Phobos (TBC)
  During Mars pointing at CA commissioning a feature tracking test is envisaged
  Rehearsal of the full timeline may take place in flight in January 2025 TBC

## Slide 16: Limitations/constraints
Hyperscout imaging timing (1 image/7 min, full ROI)
AFC imaging timing (1 image/6 seconds TBC, need CSW 1.4, max 10 images, then wait 20s, else continuous 1 image/12s, TBC)
Sun avoidance angles
  AFC Boresight (+Zsc) = +/-40°
  TIRI Boresight (+Zsc): = +/- 30, when filter wheel in measurement position, NA, when filter wheel in 'zero' position
  HyperScout Boresight (+Zsc) = +/-39°, when ON, = +/-22°, when OFF (also SEA)
Sun exclusion angles
  TIRI Boresight (+Zsc): +/-8.4 deg
Rehearsal of feature tracking is TBC

## Slide 17: MTP cycle
Introduction of an MTP cycle (Medium Term Planning)
  Produce MTP products from instrument sheets
  These products can then be checked by the scientists before actual execution
  This will be attempted with the MSB
  Idea is to find mistakes and identify misinterpretations
  Idea is NOT to allow introduction of late requests

## Slide 18: Way forward
Skeleton timeline is defined
Input on open points required
One to one discussions to take place with AFC/HYP/TIRI on excel sheet inputs
  Deadline to converge on the excel sheets is 06/12/2024 latest
  TIRI to move to event driven PORs for MSB
  In preparation for the asteroid phase too

## Slide 19: Conclusions
One to one exchanges with the instrument teams (AFC/HYP/TIRI) will resume soon (this PM!)
Need to converge by 06/12/2024
Open points need to be addressed ASAP, hopefully via the one-to-one meetings